## Jobs schedule
Jobs Follow-up - Michael Lam | [17 empty] | 2020-04-09
Invoice No. | Contract |  | Request Plan | Sent plan to Client | Permit |  | Photo |  | Order placed | Foundation ordered | Inscription |  |  |  | Accessories | Accessories | Installation booked | Remark
| signed | due |  |  | sent | back | sent | back |  |  | received | sent | signed | booked | ordered | received
RWSG523 | 2019-11-15 | N/A | 2019-07-16 | 2019-07-16 | 2019-08-13 | 2019-08-21 | TBA | - | 2019-07-05 | Done | TBA | TBA | TBA | TBA | N/A | N/A | 2019-10-03 | Installation done. Waiting for inscription content
RWSG562 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2019-09-13 | N/A | TBA | TBA | TBA | TBA | N/A | N/A | TBA | Invoice was sent to follow up the payment
RWSG619 | 2019-02-12 | N/A | 2019-07-19 | 2019-07-19 | 2019-09-20 | 2019-10-11 | - | 2019-10-11 | 2019-09-30 | Done | - | - | 2019-07-29 | Done | Candle box ordered | Candle box ordered | Done | Following up the final payment
RWSG672 | 15-Oct | N/A | 15-Oct | 16-Oct | 2019-11-04 | 2019-11-22 | 2019-11-07 | 2020-01-09 | 2019-11-28 | N/A | - | - | 2020-10-04 | - | N/A | N/A | Yes | The installation is in final stage
RWSG686 | 2019-11-25 | N/A | 2019-12-12 | 2019-12-12 | 2020-12-23 | 2020-01-08 | TBA | - | 2020-01-09 | N/A | - | - | 2020-01-08 | - | N/A | N/A | TBA | Stone arrived in Melbourne. Waiting for the delivery to Sydney after sandblasting
RWSG694 | 2019-12-12 | N/A | 2020-01-07 | 2020-01-07 | 2020-01-08 | 2020-02-05 | N/A | - | 2020-02-16 | TBA | - | - | 2020-02-12 | - | N/A | N/A | TBA | Order placed. Waiting for stone arrival
RWSG700 | 2020-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | - | 2020-01-13 | N/A | - | - | - | - | In stock | N/A | N/A | Order placed. Waiting for stone arrival
RWSG713 | 2020-02-14 | N/A | N/A | N/A | N/A | N/A | N/A | - | 2020-02-17 | N/A | - | - | - | - | In stock | N/A | N/A | Order placed. Waiting for stone arrival
RWSG729 | 2020-03-19 | N/A | N/A | N/A | 2020-03-31 | TBA | 2020-03-30 | TBA | - | N/A | 2020-03-30 | - | - | - | N/A | N/A | N/A | Permit application submitted Drawing & inscription proof to be confirmed
RWSG730 | 2020-03-20 | N/A | N/A | N/A | 2020-03-31 | TBA | N/A | - | - | N/A | 2020-03-20 | - | 2020-04-08 | - | N/A | N/A | N/A | Permit application submitted Drawing & inscription proof just signed
RWSG733 | 2020-03-25 | N/A | 2020-03-31 | TBA | 2020-03-31 | TBA | N/A | - | - | N/A | 2020-03-31 | - | - | - | N/A | N/A | N/A | Cheque received. Drawing & inscription proof to be confirmed