## Jobs schedule
Jobs Follow-up - Michael Lam | [17 empty] | 2020-05-22
Invoice No. | Contract |  | Request Plan | Sent plan to Client | Permit |  | Photo |  | Order placed | Foundation ordered | Inscription |  |  |  | Accessories | Accessories | Installation booked | Remark
| signed | due |  |  | sent | back | sent | back |  |  | received | sent | signed | booked | ordered | received
RWSG523 | 2019-11-15 | N/A | 2019-07-16 | 2019-07-16 | 2019-08-13 | 2019-08-21 | 2020-04-24 | 2020-05-13 | 2019-07-05 | Done | TBA | TBA | TBA | TBA | N/A | N/A | 2019-10-03 | Photos were received. Customer is working on the inscription
RWSG619 | 2019-02-12 | N/A | 2019-07-19 | 2019-07-19 | 2019-09-20 | 2019-10-11 | - | 2019-10-11 | 2019-09-30 | Done | - | - | 2019-07-29 | Done | Candle box ordered | Candle box ordered | Done | Following up the final payment. He came to the office and said he is trying to settle the outstanding in the next two weeks. He kept apologizing to me
RWSG686 | 2019-11-25 | N/A | 2019-12-12 | 2019-12-12 | 2020-12-23 | 2020-01-08 | 2020-12-04 | 2020-01-13 | 2020-01-09 | N/A | - | - | 2020-01-08 | Done | N/A | N/A | Yes | Inscription done in Melbourne. Will receive the monument by next week
RWSG694 | 2019-12-12 | N/A | 2020-01-07 | 2020-01-07 | 2020-01-08 | 2020-02-05 | N/A | - | 2020-02-16 | Done | - | - | 2020-02-12 | - | N/A | N/A | Yes | Will receive the monument by next week
RWSG700 | 2020-01-10 | N/A | N/A | N/A | N/A | N/A | N/A | - | 2020-01-13 | N/A | - | - | - | - | Candle box | N/A | N/A | Will receive the candle box by next week
RWSG713 | 2020-02-14 | N/A | N/A | N/A | N/A | N/A | N/A | - | 2020-02-17 | N/A | - | - | - | - | Candle box | N/A | N/A | Will receive the candle box by next week
RWSG729 | 2020-03-19 | N/A | N/A | N/A | 2020-03-31 | 2020-04-20 | 2020-03-30 | 2020-04-30 | - | N/A | 2020-03-30 | - | 2020-05-05 | - | N/A | N/A | N/A | Waiting for Dean to do the sandblasting
RWSG730 | 2020-03-20 | N/A | N/A | N/A | 2020-03-31 | 2020-04-20 | N/A | - | - | N/A | 2020-03-20 | - | 2020-04-08 | - | N/A | N/A | N/A | Permit received. Drawing & inscription proof confirmed. Order placed
RWSG733 | 2020-03-25 | N/A | 2020-03-31 | 2020-03-31 | 2020-03-31 | 2020-04-17 | 2020-05-13 | TBA | - | N/A | 2020-03-31 | - | 2020-05-13 | - | N/A | N/A | N/A | Permit received. Drawing & inscription proof confirmed. Order placed
Note: A job for additional inscription and three photos has been signed on 20 May 2020, waiting for the new invoice.