## Jobs schedule
Jobs Follow-up - Michael Lam | [17 empty] | 2020-08-07
Invoice No. | Contract |  | Request Plan | Sent plan to Client | Permit |  | Photo |  | Order placed | Foundation ordered | Inscription |  |  |  | Accessories | Accessories | Installation booked | Remark
| signed | due |  |  | sent | back | sent | back |  |  | received | sent | signed | booked | ordered | received
RWSG523 | 2019-11-15 | N/A | 2019-07-16 | 2019-07-16 | 2019-08-13 | 2019-08-21 | 2020-04-24 | 2020-05-13 | 2019-07-05 | Done | TBA | TBA | TBA | TBA | N/A | N/A | 2019-10-03 | Photos were received. Customer is working on the inscription
RWSG619 | 2019-02-12 | N/A | 2019-07-19 | 2019-07-19 | 2019-09-20 | 2019-10-11 | - | 2019-10-11 | 2019-09-30 | Done | - | - | 2019-07-29 | Done | Candle box ordered | Candle box ordered | Done | Following up the final payment.
RWSG747 | 2020-05-20 | N/A | N/A | N/A | 2020-06-17 | 2020-07-15 | 2020-06-15 | 2020-06-29 | - | N/A | 2020-05-20 | - | TBA | - | N/A | N/A | N/A | Permit received. Waiting for Dean to do the sandblasting
RWSG750 | 2020-05-27 | N/A | N/A | N/A | TBA | - | TBA | - | - | N/A | 2020-05-27 | - | TBA | - | N/A | N/A | N/A | Work permit submitted. Inscription proof English part is fine but the Chinese part yet to be received
RWSG755 | 2020-06-19 | N/A | N/A | 2020-07-02 | TBA | - | N/A | - | - | 2020-07-22 | 2020-07-23 | - | TBA | - | N/A | N/A | N/A | Drawing & inscription are fine for permit application. Waiting for the cheque
RWSG762 | 2020-06-30 | N/A | N/A | TBA | TBA | - | TBA | - | - | N/A | TBA | - | TBA | - | N/A | N/A | N/A | Drawing to be approved by customer. Working on inscription proof
RWSG766 | 2020-07-08 | N/A | N/A | TBA | TBA | - | TBA | - | - | N/A | TBA | - | TBA | - | N/A | N/A | N/A | Drawing revised. Inscription proof to be finalized by next week
RWSG767 | 2020-07-20 | N/A | N/A | TBA | TBA | - | TBA | - | - | N/A | TBA | - | TBA | - | N/A | N/A | N/A | Working on drawing
RWSG768 | 2020-07-24 | N/A | N/A | TBA | TBA | - | N/A | - | - | N/A | TBA | - | TBA | - | N/A | N/A | N/A | Working on the inscription
RWSG769 | 2020-07-28 | N/A | N/A | TBA | N/A | - | N/A | - | - | N/A | - | - | - | - | N/A | N/A | N/A | Order placed for Waverley Cemetery
RWSG770 | 2020-08-04 | N/A | N/A | TBA | TBA | - | N/A | - | - | N/A | TBA | - | TBA | - | N/A | N/A | N/A | Working on inscription