## Jobs schedule
Jobs Follow-up - Michael Lam | [17 empty] | 2020-09-18
Invoice No. | Contract |  | Request Plan | Sent plan to Client | Permit |  | Photo |  | Order placed | Foundation ordered | Inscription |  |  |  | Accessories | Accessories | Installation booked | Remark
| signed | due |  |  | sent | back | sent | back |  |  | received | sent | signed | booked | ordered | received
RWSG523 | 2019-11-15 | N/A | 2019-07-16 | 2019-07-16 | 2019-08-13 | 2019-08-21 | 2020-04-24 | 2020-05-13 | 2019-07-05 | Done | TBA | TBA | TBA | TBA | N/A | N/A | 2019-10-03 | Customer is working on the inscription
RWSG619 | 2019-02-12 | N/A | 2019-07-19 | 2019-07-19 | 2019-09-20 | 2019-10-11 | - | 2019-10-11 | 2019-09-30 | Done | - | - | 2019-07-29 | Done | Candle box ordered | Candle box ordered | Done | He said he will confirm when to pay by next Tuesday
RWSG750 | 2020-05-27 | N/A | N/A | N/A | TBA | - | TBA | - | - | N/A | 2020-05-27 | - | TBA | - | N/A | N/A | N/A | Job completed. Following up final payment
RWSG755 | 2020-06-19 | N/A | N/A | 2020-07-02 | TBA | - | N/A | - | - | 2020-07-22 | 2020-07-23 | - | 2020-07-30 | - | N/A | N/A | N/A | Permit application now with 4 signatures. The application submitted
RWSG762 | 2020-06-30 | N/A | N/A | TBA | 2020-09-03 | - | Done | - | - | N/A | TBA | - | 2020-08-12 | - | N/A | N/A | N/A | Order placed. Work permit submitted
RWSG766 | 2020-07-08 | N/A | N/A | TBA | 2020-09-10 | - | TBA | - | - | N/A | TBA | - | TBA | - | N/A | N/A | N/A | Work permit submitted
RWSG767 | 2020-07-20 | N/A | N/A | TBA | TBA | - | TBA | - | - | N/A | TBA | - | TBA | - | N/A | N/A | N/A | Working on drawing
RWSG768 | 2020-07-24 | N/A | N/A | TBA | TBA | - | N/A | - | - | N/A | TBA | - | TBA | - | N/A | N/A | N/A | Waiting for inscription proof from Dean
RWSG769 | 2020-07-28 | N/A | N/A | TBA | N/A | - | N/A | - | - | N/A | - | - | - | - | N/A | N/A | N/A | Stone arrived Melbourne, to be delivery to Sydney
RWSG770 | 2020-08-04 | N/A | N/A | TBA | TBA | - | N/A | - | - | N/A | TBA | - | TBA | - | N/A | N/A | N/A | Waiting for inscription proof from Dean
RWSG771 | 2020-08-17 | N/A | N/A | TBA | TBA | - | N/A | - | - | N/A | TBA | - | TBA | - | N/A | N/A | N/A | Waiting for inscription proof from Dean
RWSG772 | 2020-08-19 | N/A | N/A | TBA | TBA | 2020-09-01 | N/A | - | - | N/A | TBA | - | TBA | - | N/A | N/A | N/A | Job completed. Final payment received, to be confirmed
RWSG773 | 2020-08-26 | N/A | N/A | TBA | TBA | - | N/A | - | - | N/A | 2020-08-26 | 2020-09-04 | TBA | - | N/A | N/A | N/A | Purchase of a bronze plaque, inscription proof was approved