## Jobs schedule
Jobs Follow-up - Michael Lam | [17 empty] | 2020-10-16
Invoice No. | Contract |  | Request Plan | Sent plan to Client | Permit |  | Photo |  | Order placed | Foundation ordered | Inscription |  |  |  | Accessories | Accessories | Installation booked | Remark
| signed | due |  |  | sent | back | sent | back |  |  | received | sent | signed | booked | ordered | received
RWSG523 | 2019-11-15 | N/A | 2019-07-16 | 2019-07-16 | 2019-08-13 | 2019-08-21 | 2020-04-24 | 2020-05-13 | 2019-07-05 | Done | TBA | TBA | TBA | TBA | N/A | N/A | 2019-10-03 | Customer is working on the inscription
RWSG619 | 2019-02-12 | N/A | 2019-07-19 | 2019-07-19 | 2019-09-20 | 2019-10-11 | - | 2019-10-11 | 2019-09-30 | Done | - | - | 2019-07-29 | Done | Candle box ordered | Candle box ordered | Done | following up the outstanding payment
RWSG755 | 2020-06-19 | N/A | N/A | 2020-07-02 | 2020-09-22 | 2020-09-29 | N/A | - | - | Lawn | 2020-07-23 | - | 2020-07-30 | - | N/A | N/A | N/A | Installation completed. To follow up the final payment
RWSG762 | 2020-06-30 | N/A | N/A | Done | 2020-09-03 | 2020-10-07 | Done | - | - | N/A | Done | - | 2020-08-12 | - | N/A | N/A | N/A | Installation in progress
RWSG766 | 2020-07-08 | N/A | N/A | Done | 2020-09-10 | 2020-10-07 | TBA | - | - | N/A | Done | - | Done | - | N/A | N/A | N/A | Work permit received. Waiting for stone arrival.
RWSG767 | 2020-07-20 | N/A | N/A | Done | TBA | - | TBA | - | - | N/A | TBA | - | TBA | - | N/A | N/A | N/A | Drawing approved. Working on inscription
RWSG768 | 2020-07-24 | N/A | N/A | TBA | 2020-09-18 | - | N/A | - | - | N/A | TBA | - | TBA | - | N/A | N/A | N/A | Waiting for inscription proof from Dean
RWSG769 | 2020-07-28 | N/A | N/A | TBA | N/A | - | N/A | - | - | N/A | - | - | - | - | N/A | N/A | N/A | Cremation posts + vase holes delivered. To follow up the final payment
RWSG770 | 2020-08-04 | N/A | N/A | TBA | 2020-09-30 | - | N/A | - | - | N/A | TBA | - | TBA | - | N/A | N/A | N/A | Waiting for inscription proof from Dean
RWSG773 | 2020-08-26 | N/A | N/A | N/A | TBA | - | N/A | - | - | N/A | 2020-08-26 | 2020-09-04 | Done | - | N/A | N/A | N/A | Bornze plaque is ready to pick up
RWSG780 | 2020-09-14 | N/A | N/A | TBA | TBA | - | TBA | - | - | N/A | TBA | - | - | - | N/A | N/A | N/A | Working on inscription proof
RWSG782 | 2020-09-14 | N/A | N/A | TBA | 2020-10-13 | - | TBA | - | - | N/A | Done | - | Done | - | N/A | N/A | N/A | Drawing & inscription proof were approved.