## Jobs schedule
Jobs Schedule Follow-up - Michael Lam | [15 empty] | 2019-11-15
Invoice No. | Contract |  | Plan signed | Permit |  | Photo |  | Order placed | Foundation ordered | Inscription |  |  |  | Installation | Accessories | Remark
| signed | due |  | sent | back | got | ordered |  |  | got | sent | signed | booked
RWSG523 | 2019-11-15 | N/A | 2019-07-16 | 2019-08-13 | 2019-08-21 | TBA | - | 2019-07-05 | Done | TBA | TBA | TBA | TBA | 2019-10-03 | N/A | Installation done. Waiting for inscription content
RWSG552 | 2019-02-13 | N/A | 2019-04-06 | 2019-09-20 | 2019-09-23 | 2019-09-24 | 2019-09-27 | 2019-07-05 | Done | - | - | 2019-04-01 | TBA | Done | N/A | Installation completed. To follow up the final payment
RWSG562 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2019-09-13 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Stone arrived in Melbourne. Inscription proof just finished
RWSG587 | 2019-04-12 | N/A | 2019-07-26 | 2019-09-18 | 2019-09-23 | - | 2019-09-27 | TBA | TBA | 2019-08-16 | Done | Done | Done | TBA | Candle box ordered | Inscription done. Will do the installation after receiving the candle box door in early next week
RWSG588 | 2019-04-12 | N/A | 2019-09-27 | 2019-10-30 | - | - | 2019-09-27 | Done | N/A | 2019-08-16 | TBA | TBA | TBA | TBA | TBA | Permit received. Waiting for stone arrival
RWSG619 | 2019-02-12 | N/A | 2019-07-19 | 2019-09-20 | 2019-10-11 | - | 2019-10-11 | 2019-09-30 | Done | - | - | 2019-07-29 | Done | In progress | Candle box ordered | Foundation done. Inscription done. 3rd payment received. Installation in progress
RWSG653 | 2019-09-24 | N/A | 2019-10-17 | 2019-11-06 | 2019-11-14 | N/A | N/A | 2019-11-15 | TBA | - | - | - | - | TBA | TBA | Permit received. Inscription proof confirmed. Order placed
RWSG664 | 2019-09-25 | N/A | 2019-10-14 | 2019-10-30 | 2019-11-13 | N/A | 2019-10-15 | 2019-11-13 | N/A | - | - | - | - | TBA | TBA | Permit received. Order placed
RWSG668 | 2019-09-30 | N/A | N/A | 2019-10-30 | 2019-11-11 | N/A | N/A | Current stock | N/A | - | - | - | - | TBA | N/A | Permit received. inscription proof confirmed
RWSG669 | 2019-09-30 | N/A | N/A | 2019-10-30 | 2019-10-31 | N/A | 2019-10-15 | N/A | N/A | - | - | - | - | N/A | N/A | Permit received. Waiting for sandblasting on site by Dean
RWSG672 | 15-Oct | N/A | 15-Oct | 2019-11-04 | TBA | 2019-11-07 | - | TBA | TBA | - | - | - | - | TBA | TBA | Waiting for the permit
RWSG680 | 2019-11-05 | N/A | N/A | TBA | - | N/A | N/A | N/A | N/A | - | - | - | - | N/A | N/A | Deposit paid. Preparing permit application
Remark: Jobs of RWSG560, RWSG608, RWSG621 & RWSG640 initiated by Rosanna are all completed and payments are fully received.