## Jobs schedule
Jobs Schedule Follow-up - Michael Lam | [15 empty] | 2020-01-10
Invoice No. | Contract |  | Plan signed | Permit |  | Photo |  | Order placed | Foundation ordered | Inscription |  |  |  | Installation | Accessories | Remark
| signed | due |  | sent | back | got | ordered |  |  | got | sent | signed | booked
RWSG523 | 2019-11-15 | N/A | 2019-07-16 | 2019-08-13 | 2019-08-21 | TBA | - | 2019-07-05 | Done | TBA | TBA | TBA | TBA | 2019-10-03 | N/A | Installation done. Waiting for inscription content
RWSG562 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2019-09-13 | N/A | TBA | TBA | TBA | TBA | TBA | N/A | Inscription proof done. Stone returned to Melbourne for sandblasting
RWSG587 | 2019-04-12 | N/A | 2019-07-26 | 2019-09-18 | 2019-09-23 | - | 2019-09-27 | TBA | TBA | 2019-08-16 | Done | Done | Done | Done | Candle box ordered | Final payment was received on 10 Jan 2020
RWSG588 | 2019-04-12 | N/A | 2019-09-27 | 2019-10-30 | 2019-11-06 | - | 2019-09-27 | Done | N/A | 2019-08-16 | Done | Done | Done | Done | Done | Final payment was received on 10 Jan 2021
RWSG619 | 2019-02-12 | N/A | 2019-07-19 | 2019-09-20 | 2019-10-11 | - | 2019-10-11 | 2019-09-30 | Done | - | - | 2019-07-29 | Done | Done | Candle box ordered | Customer just back from overseas. He will arrange the final payment by next week
RWSG653 | 2019-09-24 | N/A | 2019-10-17 | 2019-11-06 | 2019-11-14 | N/A | N/A | 2019-11-15 | Done | - | - | - | - | Next week | N/A | Stone just arrived. Installation to be done next week
RWSG664 | 2019-09-25 | N/A | 2019-10-14 | 2019-10-30 | 2019-11-13 | N/A | 2019-10-15 | 2019-11-13 | N/A | - | - | - | - | Next week | Done | Stone just arrived. Installation to be done next week
RWSG669 | 2019-09-30 | N/A | N/A | 2019-10-30 | 2019-10-31 | N/A | 2019-10-15 | N/A | N/A | - | - | - | - | N/A | N/A | All done. Final payment has been made
RWSG672 | 15-Oct | N/A | 15-Oct | 2019-11-04 | 2019-11-22 | 2019-11-07 | - | 2019-11-28 | N/A | - | - | - | - | TBA | N/A | Waiting for stone arrival for installation
RWSG676 | - | N/A | N/A | N/A | - | N/A | N/A | N/A | N/A | Done | Done | Done | Done | N/A | N/A | Customer just collected the stone with satisfaction. Fully paid.
RWSG680 | 2019-11-05 | N/A | N/A | 2019-12-12 | - | N/A | N/A | N/A | N/A | - | - | - | 2020-01-08 | N/A | N/A | Inscription proof confirmed. Dean will do the job
RWSG686 | 2019-11-25 | N/A | 2019-12-12 | 2020-12-23 | 2020-01-08 | TBA | - | 2020-01-09 | N/A | - | - | - | - | TBA | N/A | Inscription proof confirmed. Just placed the order
RWSG694 | 2019-12-12 | N/A | 2020-01-07 | 2020-01-08 | TBA | N/A | - | TBA | TBA | - | - | - | - | TBA | N/A | Inscription proof confirmed. Waiting for the permit
Note: RWSG516 To redo the inscription on site. Dean has been scheduled for doing the job.