## Jobs schedule
Jobs Schedule Follow-up - Michael Lam | [15 empty] | 2020-03-06
Invoice No. | Contract |  | Plan signed | Permit |  | Photo |  | Order placed | Foundation ordered | Inscription |  |  |  | Installation | Accessories | Remark
| signed | due |  | sent | back | got | ordered |  |  | got | sent | signed | booked
RWSG523 | 2019-11-15 | N/A | 2019-07-16 | 2019-08-13 | 2019-08-21 | TBA | - | 2019-07-05 | Done | TBA | TBA | TBA | TBA | 2019-10-03 | N/A | Installation done. Waiting for inscription content
RWSG562 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2019-09-13 | N/A | TBA | TBA | TBA | TBA | TBA | N/A | Jacky is following up the payment
RWSG619 | 2019-02-12 | N/A | 2019-07-19 | 2019-09-20 | 2019-10-11 | - | 2019-10-11 | 2019-09-30 | Done | - | - | 2019-07-29 | Done | Done | Candle box ordered | Following up the final payment
RWSG672 | 15-Oct | N/A | 15-Oct | 2019-11-04 | 2019-11-22 | 2019-11-07 | - | 2019-11-28 | N/A | - | - | - | - | TBA | N/A | To be installed by next week
RWSG680 | 2019-11-05 | N/A | N/A | 2019-12-12 | - | N/A | N/A | N/A | N/A | - | - | - | 2020-01-08 | N/A | N/A | Following up the final payment
RWSG686 | 2019-11-25 | N/A | 2019-12-12 | 2020-12-23 | 2020-01-08 | TBA | - | 2020-01-09 | N/A | - | - | - | - | TBA | N/A | Order placed. Waiting for stone arrival
RWSG694 | 2019-12-12 | N/A | 2020-01-07 | 2020-01-08 | TBA | N/A | - | 2020-02-16 | TBA | - | - | - | - | TBA | N/A | Order placed. Waiting for stone arrival
RWSG700 | 2020-01-10 | N/A | N/A | N/A | N/A | N/A | - | 2020-01-13 | N/A | - | - | - | - | N/A | N/A | Order placed. Waiting for stone arrival
RWSG713 | 2020-02-14 | N/A | N/A | N/A | N/A | N/A | - | 2020-02-17 | N/A | - | - | - | - | N/A | N/A | Order placed. Waiting for stone arrival